## Sheet1
Sprint 2 Backlog
Team 4 - Hamish Livingston, Jo Dowdall, Ross Teviotdale, Toby Philp | [5 empty] | To Do
In Progress
Complete
Task Description | Duration time in hours | Who | Status | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday2 | Friday2 | Monday2 | Tuesday2 | Wednesday2
Set Value
Write acceptance tests | 1 | Ross | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check acceptance tests with customer | 1 | Ross | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Find each share set in live feed | 2 | Hamish | Complete | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Get value of a single share for each set in portfolio | 2 | Jo | Complete | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Display date of data retrieved | 1 | Ross | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Calculate share set values | 1 | Hamish | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Display set values | 1 | Hamish | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Round values to nearest pound | 1 | Ross | Complete | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Format values displayed using commas | 1 | Jo | Complete | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Error handling for missing stock values | 2 | Toby | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
Refactor code into separate classes | 3 | Toby | Complete | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create downloader class for current data | 1 | Ross | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Create Burndown Chart | 1 | Jo | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Record of velocity | 1 | Jo | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Unit Tests | 3 | Hamish | In Progress | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1
Prepare Team Standards | 2 | Jo | Complete | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Write Quality Assurance Report | 2 | Jo | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
Integrate Junit/Git/Eclipse | 2 | Toby | Complete | 2 | 3 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Rocket & Plummet Alerts
Write acceptance tests | 1 | Jo | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check acceptance tests with customer | 1 | Jo | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Get percentage change value from feed, for each share set | 2 | Ross | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Create pop up box | 1 | Ross | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Link pop box to share activity | 2 | Toby | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Show alert in notification bar | 4 | Jo | To Do | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Display date of activity on alert | 1 | Hamish | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Create Alert class | 2 | Toby | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Unit Tests | 2 | Ross | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
0
Run Alert
Write acceptance tests | 2 | Toby | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check acceptance tests with customer | 1 | Toby | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Create pop up box | 1 | Ross | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Get total number of shares traded for each set | 3 | Hamish | To Do | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Get total number of shares available for each company | 2 | Ross | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Link pop box to share activity | 2 | Toby | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Show alert in notification bar | 1 | Jo | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Display date of activity on alert | 1 | Hamish | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Calculation to detect a run | 1 | Ross | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Unit Tests | 2 | Toby | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Total Hours Remaining | 60 |  |  | 55 | 50 | 49 | 46 | 41 | 41 | 40 | 34 | 31 | 30
Total hours per person | Name | Hours Work Remaining
| Hamish | 6
| Jo | 6
| Ross | 9
| Toby | 9