## Sheet1
Sprint 1 Backlog
Team 4 - Hamish Livingston, Jo Dowdall, Ross Teviotdale, Toby Philp | [5 empty] | To Do
In Progress
Complete
Task Description | Duration time in hours | Who | Status | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday2 | Friday2 | Monday2 | Tuesday2 | Wednesday2
1. Establish Feeds Into App
Create App Template | 1 | Jo | Complete | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Find and Evaluate feed options | 3 | Hamish | Complete | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Research API for feed | 1 | Hamish | Complete | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Research Android API for data connections | 2 | Toby | Complete | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement Class that connects to and retrieves from data feed | 5 | Ross | Complete | 5 | 5 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 0
Error handling for no connection | 1 | Toby | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Write acceptance test | 1 | Hamish | Complete | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Verify task complete with Client | 1 | Jo | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Create GUI that displays BP share price | 1 | Toby | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
2. Total Portfolio Value
Design Interface | 1 | Jo | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Retrieve Individual share price for each company as of previous Friday | 1 | Toby | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 0 | 0
Calculate Worth of Portfolio | 2 | Hamish | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0
Display total value | 2 | Jo | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0
Format total value with commas | 1 | Ross | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Write acceptance test | 1 | Hamish | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Error handling for missing stock values | 2 | Toby | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 0 | 0
Use calander to find previous Friday | 2 | Jo | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
Verify task complete with client | 1 | Ross | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Total Hours Remaining | 29 |  |  | 29 | 27 | 24 | 21 | 19 | 18 | 18 | 12 | 2 | 0
Total hours per person | Name | Hours Work Remaining
| Hamish | 0
| Jo | 0
| Ross | 0
| Toby | 0